## Matsobane Khwinana
ELEN-7046 Group Project – Individual Time sheet - Matsobane Khwinana
Task | Date | Start Time | End Time | Estimated Hours | Actual Hours
Data Collection : Studying the Twitter API | 2016-04-22 | 10:13 | 11:13 | 2 | 1:00
Data Collection : Playing with Twitter API | 2016-04-23 | 11:25 | 13:15 | 2 | 1:50
Data Collection : Writing Java Twitter API client (POC) | 2016-04-23 | 15:00 | 18:00 | 2 | 3:00
Project Group Meeting 1 | 2016-04-24 | 14:30 | 16:30 | 2 | 2:00
Data Collection : Fixing the POC – streaming issue | 2016-04-27 | 10:00 | 12:00 | 6 | 2:00
Data Collection : Mapping Twitter JSON payload to simple tweet object | 2016-04-27 | 14:45 | 16:45 | 4 | 2:00
Data Collection : Mapping Twitter JSON payload to simple tweet object | 2016-04-28 | 14:00 | 15:00 | 1 | 1:00
Data Collection : Fixing the geo-location mapping issues | 2016-04-29 | 9:30 | 10:30 | 2 | 1:00
Installed Apache Hadoop | 2016-05-01 | 12:00 | 13:00 | 1 | 1:00
Project Group Meeting 3 | 2016-05-08 | 14:30 | 16:30 | 2 | 2:00
Data Collection : Reading up on Apache Hadoop and doing tutorial examples | 2016-05-02 | 9:30 | 11:30 | 4 | 2:00
Data Collection : Reading up on MongoDB, Installed MongoDB and Tutorial on MongoDB Java Driver | 2016-05-02 | 15:40 | 17:00 | 2 | 1:20
Project Group Meeting 4 | 2016-05-15 | 14:30 | 16:30 | 2 | 2:00
Data Collection : Making Java stored Mongo data in BSON format to match with the C# counterpart | 2016-05-16 | 19:15 | 21:30 | 1 | 2:15
Data Collection : Re-factored the Java Data Extraction Service | 2016-05-18 | 8:00 | 10:00 | 2 | 2:00
Data Collection : Fixed MongoDB records printing settings | 2016-05-18 | 20:00 | 21:30 | 2 | 1:30
Data Collection : Fixed Tweet URL determination issue | 2016-05-19 | 9:30 | 11:30 | 2 | 2:00
Data Collection : Added default location lookup, Removed Polygon location support, other bug fixes | 2016-05-21 | 20:00 | 23:00 | 4 | 3:00
Project Group Meeting 5 | 2016-05-22 | 14:30 | 16:30 | 2 | 2:00
UI : Learning: Introduction to Node.js, installations and setup | 2016-05-22 | 19:00 | 21:30 | 2 | 2:30
UI : Learning: Node.js basic concepts videos | 2016-05-23 | 20:00 | 22:15 | 2 | 2:15
UI : Learning: Node.js basic concepts videos | 2016-05-24 | 18:30 | 20:30 | 2 | 2:00
UI : Induction to the ELEN7046 Group Web module with Dave Cloete | 2016-05-26 | 17:47 | 18:50 | 1 | 1:03
UI : Learning: Tutorials on Node.js Web module and the Express web framework | 2016-05-27 | 18:00 | 21:00 | 3 | 3:00
UI : Learning: A brief in introduction to Twig and D3 visualisation framework | 2016-05-28 | 9:15 | 10:30 | 2 | 1:15
Project Group Meeting 6 | 2016-06-05 | 12:00 | 18:00 | 4 | 6:00
UI : Con vs Pro Bar Chart | 2016-06-06 | 18:40 | 21:50 | 2 | 3:10
UI : Con vs Pro Bar Chart | 2016-06-07 | 10:30 | 12:00 | 2 | 1:30
UI : Con vs Pro Bar Chart | 2016-06-09 | 18:00 | 21:00 | 2 | 3:00
Project Group Meeting 7 | 2016-06-11 | 10:00 | 19:00 | 2 | 9:00
Reformatting the data stored in MongoDB to pure JSON to use by Spark engine | 2016-06-15 | 10:30 | 13:30 | 2 | 3:00
Converting the historic data extraction service to Java Enterprise version | 2016-06-16 | 14:00 | 16:00 | 2 | 2:00
Converting the historic data extraction service to Java Enterprise version | 2016-06-16 | 18:00 | 23:00 | 3 | 5:00
Re-factored and refine Data Extraction Service use case implementation | 2016-06-17 | 10:30 | 14:30 | 2 | 4:00
Project Group Meeting 8 | 2016-06-18 | 9:00 | 21:00 | 8 | 12:00
Project Group Meeting 9 | 2016-06-19 | 9:00 | 13:00 | 2 | 4:00
Project Group Meeting 10 | 2016-06-26 | 14:30 | 17:30 | 2 | 3:00
Group Report | 2016-06-28 | 18:00 | 20:00 | 3 | 2:00
Group and Individual Report | 2016-06-29 | 18:30 | 23:30 | 8 | 5:00
Group Meeting 11(Virtual) | 2016-06-30 | 18:30 | 20:00 | 1 | 1:30
Project Group Meeting 12 | 2016-07-01 | 10:00 | 17:00 | 8 | 7:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
|  |  |  | 110 | 118:08
Data Collection : Studying the Twitter API | 2016-04-22
Data Collection : Playing with Twitter API | 2016-04-23
Data Collection : Writing Java Twitter API client (POC) | 2016-04-23