## Gareth Stephenson
ELEN-7046 Group Project – Individual Time sheet - Gareth Stephenson
Task | Date | Start Time | End Time | Estimated Hours | Actual Hours
Create PI network with 2 nodes | 2016-04-22 | 18:00 | 22:00 | 4 | 4:00
Modify PC ATX PSU to work with PI's | 2016-04-23 | 12:00 | 18:00 | 6 | 6:00
Project Group Meeting 1 | 2016-04-24 | 14:30 | 16:30 | 2 | 2:00
Expand PI network with 2 nodes | 2016-04-25 | 19:00 | 23:00 | 2 | 4:00
Trying to install Hadoop on PI cluster | 2016-04-27 | 9:00 | 17:00 | 4 | 8:00
Trying to install Apache Spark on PI cluster on 4 nodes | 2016-04-28 | 18:00 | 23:00 | 4 | 5:00
Added extra node to the PI cluster, installed Hadoop and Spark on node | 2016-04-29 | 18:00 | 23:00 | 4 | 5:00
Project Group Meeting 2 | 2016-05-01 | 14:30 | 16:30 | 2 | 2:00
Learning scala and by working writing word count app, fine tuning Apache Spark | 2016-05-02 | 18:00 | 21:00 | 3 | 3:00
Learning scala and by working writing word count app, fine tuning Apache Spark | 2016-05-03 | 18:00 | 21:00 | 3 | 3:00
Learning scala and by working writing word count app, fine tuning Apache Spark | 2016-05-04 | 21:00 | 22:00 | 2 | 1:00
Learning scala and by working writing word count app, fine tuning Apache Spark | 2016-05-05 | 18:00 | 21:00 | 3 | 3:00
Started CategoryCountPerHour program | 2016-05-06 | 18:00 | 21:00 | 3 | 3:00
Working on CategoryCountPerHour program | 2016-05-07 | 10:00 | 22:00 | 8 | 12:00
Project Group Meeting 3 | 2016-05-08 | 14:30 | 16:30 | 2 | 2:00
Working on CategoryCountPerHour program | 2016-05-09 | 18:00 | 22:00 | 4 | 4:00
Running twitter data through the Scala CategoryCountPerHour program | 2016-05-10 | 18:00 | 23:00 | 4 | 5:00
Calibrating CategoryCountPerHour program based on twitter data using SparkSQL | 2016-05-11 | 21:00 | 23:00 | 2 | 2:00
Calibrating CategoryCountPerHour program based on twitter data using SparkSQL | 2016-05-12 | 18:00 | 22:00 | 4 | 4:00
Calibrating CategoryCountPerHour program based on twitter data using SparkSQL | 2016-05-13 | 18:00 | 23:00 | 5 | 5:00
Calibrating CategoryCountPerHour program based on twitter data using SparkSQL | 2016-05-14 | 10:00 | 22:00 | 8 | 12:00
Project Group Meeting 4 | 2016-05-15 | 14:30 | 16:30 | 2 | 2:00
Calibrating CategoryCountPerHour program based on twitter data using SparkSQL | 2016-05-16 | 18:00 | 23:00 | 3 | 5:00
Calibrating CategoryCountPerHour program based on twitter data using SparkSQL | 2016-05-17 | 18:00 | 23:00 | 3 | 5:00
Master node failure, rebuilding Apache Spark master | 2016-05-21 | 9:00 | 21:00 | 9 | 12:00
Project Group Meeting 5 | 2016-05-22 | 14:30 | 16:30 | 2 | 2:00
Moving away from Apache SparkSQL, trying to use object based map reduce | 2016-05-23 | 18:00 | 20:00 | 2 | 2:00
Moving away from Apache SparkSQL, trying to use object based map reduce | 2016-05-28 | 10:00 | 22:00 | 4 | 12:00
Moving away from Apache SparkSQL, trying to use object based map reduce | 2016-05-29 | 12:00 | 20:00 | 4 | 8:00
Moving away from Apache SparkSQL, trying to use object based map reduce | 2016-05-30 | 18:00 | 20:00 | 2 | 2:00
Moving away from Apache SparkSQL, trying to use object based map reduce | 2016-05-31 | 18:00 | 20:00 | 2 | 2:00
Moving away from Apache SparkSQL, trying to use object based map reduce | 2016-06-02 | 18:00 | 20:00 | 2 | 2:00
Project Group Meeting 6 | 2016-06-05 | 12:00 | 18:00 | 2 | 6:00
Got CategoryCountPerHour program to use object based map reduce | 2016-06-07 | 18:00 | 20:00 | 2 | 2:00
Got CategoryCountPerHour program to use object based map reduce | 2016-06-09 | 18:00 | 20:00 | 2 | 2:00
Got CategoryCountPerHour program to use object based map reduce | 2016-06-10 | 18:00 | 20:00 | 2 | 2:00
Project Group Meeting 7 | 2016-06-11 | 10:00 | 19:00 | 2 | 9:00
Working on CategoryCountPerDay program | 2016-06-12 | 18:00 | 20:00 | 2 | 2:00
Working on CategoryCountPerDay program | 2016-06-13 | 18:00 | 20:00 | 2 | 2:00
Working on CategoryCountPerDay program | 2016-06-14 | 18:00 | 20:00 | 2 | 2:00
Working on CategoryCountPerDay program | 2016-06-16 | 18:00 | 20:00 | 2 | 2:00
Working on CategoryCountPerDay program | 2016-06-17 | 18:00 | 20:00 | 2 | 2:00
Project Group Meeting 8 | 2016-06-18 | 9:00 | 21:00 | 8 | 12:00
Project Group Meeting 9 | 2016-06-19 | 9:00 | 13:00 | 2 | 4:00
Working on CategoryCountPerDay program | 2016-06-20 | 18:00 | 20:00 | 2 | 2:00
Working on CategoryCountPerDay program | 2016-06-21 | 18:00 | 20:00 | 2 | 2:00
Group Presentation | 2016-06-22 |  |  |  | 0:00
Working on CategoryCountPerDay program | 2016-06-23 | 18:00 | 20:00 | 2 | 2:00
Working on CategoryCountPerDay program | 2016-06-24 | 18:00 | 20:00 | 2 | 2:00
Project Group Meeting 10 | 2016-06-26 | 14:30 | 17:30 | 2 | 3:00
Working on Group Report | 2016-06-27 |  |  |  | 0:00
Working on Group Report | 2016-06-28 |  |  |  | 0:00
Working on Group Report | 2016-06-29 |  |  |  | 0:00
Group Meeting 11(Virtual) | 2016-06-30 | 18:30 | 20:00 | 1 | 1:30
Project Group Meeting 12 | 2016-07-01 | 10:00 | 17:00 | 8 | 7:00
|  |  |  | 163 | 205:30