## Twit-Con-Pro Team
ELEN-7046 Group Project – Combined Time sheet
Task | Start Date | End Date | Duration
Business Modelling
- Research Technologies | 42480 | 42512 | 32
- Business Case | 42484 | 42491 | 7
Requirements
- Use-Case Model | 42491 | 42498 | 7
- POC / Prototyping | 42484 | 42512 | 28
- Specifications | 42491 | 42512 | 21
- Review | 42512 | 42512 | 0
Analysis & Design
- Software Architecture Description | 42505 | 42512 | 7
- Component Design | 42505 | 42512 | 7
Implementation
- Development | 42512 | 42540 | 28
Testing
- Component/Unit Testing | 42512 | 42540 | 28
Deployment
- Demonstration (Description of current release / Roll-out the project to the market) | 42539 | 42543 | 4
Supporting
- Project Management | 42484 | 42552 | 68
- Documentation Deliverable | 42547 | 42552 | 5