## Sidwell
ELEN-7046 Group Project – Individual Time sheet - Sidwell Mokhemisa
Task | Date | Start Time | End Time | Estimated Hours | Actual Hours
Project Group Meeting 1 | 2016-04-24 | 14:30 | 16:30 | 2 | 2:00
Start High Level Design Activities | 2016-04-28 | 9:00 | 17:00 | 8 | 8:00
Project Group Meeting 2 | 2016-05-01 | 14:30 | 16:30 | 2 | 2:00
Start Use Case Modeling | 2016-05-02 | 17:30 | 21:30 | 10 | 4:00
Complete Use Case Modeling | 2016-05-07 | 10:00 | 15:00 | 8 | 5:00
Project Group Meeting 3 | 2016-05-08 | 14:30 | 16:30 | 2 | 2:00
Identify Delivery Method (SDLC) | 2016-05-14 | 10:00 | 13:00 | 4 | 3:00
Project Group Meeting 4 | 2016-05-15 | 14:30 | 16:30 | 2 | 2:00
Deliver a Tailored Method based on RUP | 2016-05-16 | 16:00 | 22:00 | 3 | 6:00
Project Group Meeting 5 | 2016-05-22 | 14:30 | 16:30 | 2 | 2:00
Component Model | 2016-05-23 | 18:00 | 21:00 | 9 | 3:00
Project Group Meeting 6 | 2016-06-05 | 12:00 | 18:00 | 2 | 6:00
Infrastructure Deign | 2016-06-06 | 18:00 | 22:00 | 6 | 4:00
Project Group Meeting 7 | 2016-06-11 | 10:00 | 19:00 | 2 | 9:00
Project Group Meeting 8 | 2016-06-18 | 9:00 | 21:00 | 8 | 12:00
Project Group Meeting 9 | 2016-06-19 | 9:00 | 13:00 | 2 | 4:00
Project Presentation Deck | 2016-06-19 | 14:00 | 18:00 | 3 | 4:00
Project Group Meeting 10 | 2016-06-26 | 14:30 | 17:30 | 2 | 3:00
Reports - Individual and Group | 2016-06-30 | 9:00 | 18:30 | 16 | 9:30
Group Meeting 11(Virtual) | 2016-06-30 | 18:30 | 20:00 | 1 | 1:30
Project Group Meeting 12 | 2016-07-01 | 10:00 | 17:00 | 8 | 7:00
Individual Report | 2016-07-02 | 10:00 | 22:00 | 11 | 12:00
|  |  |  | 113 | 111:00