## Sheet1
Core-Process Workflows | Inception Phase | Tailoring | Elaboration Phase | Tailoring | Construction Phase | Tailoring | Transition Phase | Tailoring
Business Model | Vision Document | N/A
| A Business Model | N/A
| An Initial Business Case | N/A
Requirements | Initial Use-Case Model | T | A Use-Case Model | T
| One or Several Prototypes | T | Supplementary Requirements Capturing (NFR) | T
Analysis and Design |  |  | A Software Architecture Description | I
Implementation |  |  | An Executable Architectural Prototype | T | Sofware Product Integrated on adequate platforms | I
Test | [6 empty] | Beta Testing | T
Deployment |  |  |  |  | A description of current release | T | Roll-out the project to the market | I
[7 empty] | Parallel operation with legacy system | N/A
[7 empty] | Conversion of operational databases | N/A
Core Supporting Workflows
Config & Change Management |  |  | A Preliminary User Manual (Optional) | N/A | The User Manuals | N/A | Training of users and maintainers | N/A
Project Management | An Initial Rist Assessment | T | A Revised Risk List and business case | T
| A Project Plan Showing Phases and Iterations | T | A development plan for overall of project | T
| An Initial Project Glossary (Domain Model) | N/A | An Updated development case specifying process to follow | T
Environment